## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Ordering Experience: The majority of customers (82%) ordered appetizers, and 100% ordered dinner, indicating a high level of engagement with the tablet ordering system. | 1. During your visit, what did you order? Choose all that apply. Drinks 28 56% Appetizers 41 82% Dinner 50 100% Dessert 35 70% - This data point shows a high level of engagement with the tablet ordering system, with a significant percentage of customers ordering various items. | Continuously update and diversify the menu options on the tablet to cater to different customer preferences and maintain a wide selection of items.
Customers | Went well | Efficient Check-Out Process: 82% of customers agreed that the checkout process was quick, easy, and secure, demonstrating a smooth transaction experience. | 10. How would you respond to the following sentence: 'I found the checkout process quick, easy, and secure.' True 41 82% - This response indicates that a majority of customers found the check-out process smooth and efficient. | Implement measures to further streamline the check-out process, such as enabling additional payment options, addressing technical issues, and optimizing the system for faster transactions.
Customers | Went well | Positive Feedback on Tablet Experience: 72% of customers rated their overall experience with the tablet as 4 or 5, indicating a favorable reception to the tablet system. | 3. On a scale of 1-5, please rate your experience with the tablet overall. 4 20 40% 5 - Great 16 32% - This survey response highlights that a significant portion of customers had a positive overall experience with the tablet system. | Continue to gather customer feedback and use it to make iterative improvements to the tablet interface, performance, and overall user experience. Regularly assess and address any concerns or issues raised by customers.
Customers | Needs improvement | Tablet Navigation and Ease of Use: While 40% of customers rated tablet navigation as easy, 52% expressed difficulty or neutrality. Improving the intuitiveness and user-friendliness of the tablet interface would enhance the overall user experience. | 5. On a scale of 1-5, how easy was it to use the tablet navigation? 1 - Difficult 2 4% 2 9 18%, 3 - Neutral 15 30% - This survey response indicates that a significant portion of customers found the tablet navigation to be difficult or had a neutral opinion. | Conduct user testing and gather feedback to identify specific pain points in tablet navigation. Based on the feedback, refine the user interface, enhance the intuitiveness of the system, and provide clear instructions or tutorials to assist customers in navigating the tablet smoothly.
Customers | Needs improvement | Waiter Instructions and Assistance: Only 76% of customers felt that waiters instructed them well on using the tablets. Providing comprehensive training to waitstaff and ensuring they can effectively guide customers in utilizing the tablets would help address any confusion or issues. | 4. How well did your waiter instruct you how to use the tablet? 1 - Not well 5 10%, 2 7 14%, 3 - Very well 38 76%". - While the majority of customers felt that the waiters provided good instructions, a significant portion had mixed experiences or felt the instructions were lacking. | Provide comprehensive training to waitstaff regarding the tablet system, ensuring they are well-versed in its features and functionality. Encourage waiters to proactively assist customers with using the tablets, addressing any questions or concerns that may arise.
Customers | Needs improvement | Technical Issues: Although only 12% of customers reported technical issues with the tablets, the freezing and glitchy experiences mentioned in the comments indicate areas for improvement. Ensuring tablet stability and regular maintenance would prevent such issues and enhance customer satisfaction. | 15. Did you have any technical issues with your tablet? No 44 88% Yes 6 12% - Although the majority did not experience technical issues, a notable percentage of customers faced challenges with freezing or glitchy tablets. | Regularly maintain and update the tablet hardware and software to minimize technical issues. Provide a mechanism for customers to report any technical problems they encounter and promptly address these issues through troubleshooting, repair, or replacement.
Project team | Went well | Tablet Installation and Functionality | "We got all the tablets installed and working at my location." - Alex (General Manager, Downtown) | Ensure consistent and efficient installation of tablets across all locations during future rollouts. Establish a clear process and schedule for tablet installation, including thorough testing and troubleshooting to minimize any technical issues.
Project team | Went well | Guest Adaptation to Tablets | "It seemed like all the guests got the hang of the tablets." - Gilly (General Manager, North) | Continue to provide clear instructions and guidance to guests on how to use the tablets effectively. Monitor guest feedback and address any common usability issues. Consider offering additional on-site support or assistance for guests who may have difficulty adapting to the new technology.
Project team | Went well | Smooth Ticket Flow | "Tickets came through at a good pace and were easy to keep track of." - Zane (Kitchen Manager, North) | Maintain efficient ticket flow by regularly monitoring the kitchen operations and ticket management system. Address any bottlenecks or issues promptly. Consider implementing automated systems or tools to further streamline the ticket flow process, such as kitchen display systems or digital order tracking.
Project team | Needs improvement | Table Turn Time | "One area we could still improve is table turn time. We didn’t see as much of a decrease as we wanted to in that area." - Gilly (General Manager, North) | Conduct a comprehensive analysis of the factors impacting table turn time, including staff workflow, kitchen operations, and customer behavior. Identify opportunities to optimize processes, such as improving communication between front and back of house, streamlining order taking and delivery, and implementing time-saving measures in food preparation. Provide additional training or resources to staff members involved in table turn processes.
Project team | Needs improvement | Food Orders Sent Back | "Even though the ticket flow was smooth, there were still orders that got sent back. So, that’s still an issue that needs to be addressed." - Zane (Kitchen Manager, North) | Investigate the root causes of food orders being sent back, such as miscommunication, preparation errors, or quality control issues. Strengthen training programs for kitchen staff, emphasizing consistent quality standards, accurate order preparation, and attention to customer preferences. Improve communication channels between the kitchen and front of house to ensure accurate order transmission and minimize errors.
Project team | Needs improvement | Technical Issues during POS Integration | "We discovered a few technical issues during the POS integration process. The good part is that we were able to address them quickly and get them fixed!" - Seydou (Restaurant Consultant) | Conduct a thorough review of the POS integration process to identify and address the technical issues encountered. Collaborate closely with the technical team to implement robust solutions and preventive measures. Update the process manual with clear instructions and troubleshooting steps for common technical issues. Regularly perform maintenance checks and updates to minimize future disruptions and ensure a seamless experience for both staff and customers.